## 分阶段 by phase
阶段 phase | 起止 dates | 人时 (h) | API次数 calls | 输入 tokens | 输出 tokens | cache read | 总 tokens | 花费 USD | 花费 CNY | 模型 models | 工具 tools
P0 立项 · 调研与设计 | 2026-08-30 … 2026-09-08 | 19.7 | 4402 | 34716986 | 2193396 | 705602560 | 742512942 | 36.0503 | 259.5621 | glm-5.3-flash 3883 · DeepSeek-V4-Flash-0731 284 · glm-5.2 183 · GLM-5.3-Flash 46 · deepseek-v4-flash-free 6 | bash 1526 · read 1484 · grep 545 · edit 348 · web_search 334 · advise 232
P1 M1+M2 核心引擎 | 2026-09-09 … 2026-09-09 | 10.37 | 3139 | 19372666 | 2237328 | 559675840 | 581285834 | 15.1942 | 109.3981 | DeepSeek-V4-Flash-0731 1702 · GLM-5.3-Flash 1437 | bash 1186 · read 959 · edit 640 · eval 300 · grep 150 · hub 135
P2 M3+M4 GUI 与 Agent | 2026-09-10 … 2026-09-10 | 1.95 | 403 | 3939204 | 282388 | 69796864 | 74018456 | 2.1356 | 15.376 | DeepSeek-V4-Flash-0731 282 · GLM-5.3-Flash 121 | read 148 · bash 128 · edit 77 · eval 53 · grep 41 · hub 30
P3 M5 交付与收尾 | 2026-09-12 … 2026-09-13 | 4.83 | 3099 | 15325343 | 2442188 | 238025088 | 255792619 | 0 | 0 | DeepSeek-V4.1-Flash 3099 | bash 2370 · read 944 · eval 476 · edit 367 · grep 129 · write 59
合计 TOTAL | 2026-08-30 … 2026-09-13 | 36.85 | 11043 | 73354199 | 7155300 | 1573100352 | 1653609851 | 53.38 | 384.3362

## 逐日 daily
日期 date | 阶段 phase | 人时 h | API次数 calls | 输入 tokens | 输出 tokens | cache read | 总 tokens | 花费 USD | 花费 CNY
2026-08-30 | P0 | 6.95 | 2106 | 11162106 | 1130358 | 212327872 | 224620336 | 10.6761 | 76.8681
2026-08-31 | P0 | 4.77 | 751 | 10277436 | 352072 | 179600192 | 190229700 | 7.8683 | 56.6516
2026-09-01 | P0 | 5.31 | 1305 | 11076472 | 463075 | 273644224 | 285183771 | 15.9768 | 115.0328
2026-09-06 | P0 | 0.08 | 14 | 47088 | 5106 | 394496 | 446690 | 0.0238 | 0.1716
2026-09-07 | P0 | 1.41 | 94 | 535295 | 118538 | 7745152 | 8398985 | 0.3888 | 2.7991
2026-09-08 | P0 | 1.16 | 132 | 1618589 | 124247 | 31890624 | 33633460 | 1.1165 | 8.0389
2026-09-09 | P1 | 10.37 | 3139 | 19372666 | 2237328 | 559675840 | 581285834 | 15.1942 | 109.3981
2026-09-10 | P2 | 1.95 | 403 | 3939204 | 282388 | 69796864 | 74018456 | 2.1356 | 15.376
2026-09-12 | P3 | 3.21 | 2418 | 11825374 | 1602010 | 186828160 | 200255544 | 0 | 0
2026-09-13 | P3 | 1.62 | 681 | 3499969 | 840178 | 51196928 | 55537075 | 0 | 0
合计 TOTAL |  | 36.85 | 11043 | 73354199 | 7155300 | 1573100352 | 1653609851 | 53.38 | 384.3362

## 工具 tools
工具 tool | P0 | P1 | P2 | P3 | 合计 total
bash | 1526 | 1186 | 128 | 2370 | 5210
read | 1484 | 959 | 148 | 944 | 3535
edit | 348 | 640 | 77 | 367 | 1432
eval | 160 | 300 | 53 | 476 | 989
grep | 545 | 150 | 41 | 129 | 865
web_search | 334 | 0 | 0 | 7 | 341
write | 52 | 126 | 3 | 59 | 240
advise | 232 | 0 | 0 | 0 | 232
hub | 41 | 135 | 30 | 17 | 223
todo | 52 | 77 | 8 | 23 | 160
glob | 82 | 29 | 4 | 7 | 122
yield | 44 | 36 | 4 | 12 | 96
ask | 18 | 5 | 0 | 4 | 27
task | 8 | 14 | 2 | 1 | 25
learn | 4 | 3 | 0 | 0 | 7
goal | 2 | 0 | 0 | 0 | 2
合计 total | 4932 | 3660 | 498 | 4416 | 13506

## 方法 method
项目 item | 说明 detail
项目 project | Disk Janitor / 还我磁盘 Giveback
课程 course | 程序设计训练（Rust 语言）30240522-3, THU CS
交付物 deliverable | AI 开发开销明细表（分阶段: 人时 / API次数 / tokens / 花费 / 模型 / 工具）
数据来源 source | omp session transcripts: ~/.omp/agent/sessions/-Code-disk_janitor
语料 corpus | 16 top-level sessions + 132 subagent transcripts
快照 cutoff | 2026-09-13 15:00 +08:00 (2026-09-13 07:00 UTC) — the newest activity in the corpus. The generator is deterministic w.r.t. the corpus, so re-running after new work moves the figures; both artifacts move together.
人时方法 person-hours method | Union of every activity window across the transcripts; timestamps sorted, a gap > 20 minutes splits a segment; segments merged globally so overlapping sessions count once. Each segment is attributed to the phase of its start day. This is a DERIVED figure, not observed human hours.
人时合计 total | 36.8452 h over 22 segments
汇率 FX | CNY = USD x 7.2 — the same static rate the product's own cost::USD_CNY uses (D-20), not a live FX feed
caveat 1 | omp only — Claude Code / OpenCode / Kimi Code sessions are NOT counted.
caveat 2 | Snapshot: the transcript corpus is frozen at the cutoff above and keeps growing, so re-running the generator moves the numbers.
caveat 3 | P3 (DeepSeek-V4.1-Flash) reports $0.00 because its gateway publishes no per-token price. Its token counts are real; $0.00 is a reporting gap, not free usage.
caveat 4 | ~/.omp/agent/agent.db is NOT usable (usage_cost_history is all a retired provider with NULL timestamps; client_usage is empty). The transcript JSONL is the authority.
caveat 5 | cacheWrite is 0 on every record — this gateway bills cache reads only.
runtime ledger | Separate quantity: the shipped binary's own LLM spend (Kind::Budget records, D-20). Currently empty — see docs/expense-sheet.md §6.